## Sheet1
TASK | BEGIN | TIME
planning | 0 | 5
life forms | 1 | 2
Predator/prey | 1 | 2
Biomes | 2 | 2
Apocalypse | 5 | 2
TRAIN! | 5 | 3
GUI | 5 | 15
Weather | 6 | 6
Disease | 7 | 9
Natural disasters | 8 | 5
Mordor | 10 | 2
Different views | 10 | 10
Fellowship | 11 | 2
Board | 13 | 3
Change landscape, add lifeforms | 14 | 12
Panning | 15 | 20
testing | 20 | 15
Menu | 29 | 6
total | 35 days from the 16th